## Project Tracking
AGILE SOFTWARE ENGINEERING | [9 empty] | STATUS KEY | PRIORITY KEY
[10 empty] | On Hold | Low
PROJECT TITLE |  | SPORTACUS | [7 empty] | Not Yet Started | Medium
PROJECT MANAGER |  | Dennis Lee |  |  |  |  | SPRINT 1 | 5/16/2022 - 5/30/2022 |  | In Progress | High
SCRUM MASTER |  | Eric Drejza |  |  |  |  | SPRINT 2 | 5/31/2022 - 6/13/2022 |  | In Progress | High
DEVELOPERS |  | Travis Biggs, Jeff Lehman, Joe Hammer, Brett Conti, Alex Caruso |  |  |  |  | SPRINT 3 | 6/14/2022 - 6/27/2022 |  | In Progress | High
PROJECT DETAILS | [7 empty] | DELIVERABLES
STATUS | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE
SPRINT 1 - Connect to API and pull relevant data into CSV | [8 empty] | 0%
Not Yet Started | High | 2022-05-16 | 2022-05-30 | 14 | <SPORT> API | Travis | Pick a sport and make an API connection and pull data from that connection |  | 0%
Not Yet Started | High | 2022-05-16 | 2022-05-30 | 14 | <SPORT> API | Jeff | Pick a sport and make an API connection and pull data from that connection |  | 0%
Not Yet Started | High | 2022-05-16 | 2022-05-30 | 14 | <SPORT> API | Joe | Pick a sport and make an API connection and pull data from that connection |  | 0%
Not Yet Started | High | 2022-05-16 | 2022-05-30 | 14 | <SPORT> API | Brett | Pick a sport and make an API connection and pull data from that connection |  | 0%
Not Yet Started | High | 2022-05-16 | 2022-05-30 | 14 | <SPORT> API | Alex | Pick a sport and make an API connection and pull data from that connection |  | 0%
SPRINT 2 - TBD | [8 empty] | 0%
Not Yet Started | High | 2022-05-16 | 2022-05-30 | 14 |  | Travis | Details of task here |  | 0%
Not Yet Started | High | 2022-05-16 | 2022-05-30 | 14 | Task | Jeff | Details of task here |  | 0%
Not Yet Started | High | 2022-05-16 | 2022-05-30 | 14 | Task | Joe | Details of task here |  | 0%
Not Yet Started | High | 2022-05-16 | 2022-05-30 | 14 | Task | Brett | Details of task here |  | 0%
Not Yet Started | High | 2022-05-16 | 2022-05-30 | 14 | Task | Alex | Details of task here |  | 0%